## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Chatbot-Pizza Ordering |  |  |  |  | INSTITUTE NAME | [6 empty] | A.P.Shah Institute of Technology
PROJECT GUIDE |  | Prof. Archana Kotangale |  |  |  |  | DATE | [6 empty] | 2019-07-27
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Sayali Kamble | 2019-07-26 | 2019-08-02 | 1 | 100% | bar: WEEK 1 F to WEEK 2 W
1.1.1 | Research paper finalization | Zahid Khan | 2019-07-26 | 2019-08-02 | 1 | 100% | bar: WEEK 1 F to WEEK 2 F
1.2 | Project Title | Sayali, Zahid, Vishal | 2019-07-26 | 2019-08-02 | 1 | 100% | bar: WEEK 2 F
1.3 | Abstract | Vishal Jain | 2019-08-03 | 2019-08-16 | 2 | 100% | bar: WEEK 3 M to WEEK 3 R
1.4 | Objectives | Zahid Khan | 2019-08-03 | 2019-08-16 | 2 | 100% | bar: WEEK 3 W to WEEK 3 F
1.5 | Literature Review | Sayali Kamble | 2019-08-03 | 2019-08-16 | 2 | 100% | bar: WEEK 3 F to WEEK 4 F
1.6 | Problem Definition | Sayali, Zahid, Vishal | 2019-08-03 | 2019-08-16 | 2 | 100% | bar: WEEK 4 R to WEEK 4 F
1.7 | Scope | Zahid Khan | 2019-08-17 | 2019-08-23 | 1 | 100% | bar: WEEK 5 M to WEEK 5 T
1.8 | Technology stack | Vishal, Sayali, Zahid | 2019-08-17 | 2019-08-23 | 1 | 80% | bar: WEEK 5 T to WEEK 5 R
1.9 | Benefits for society | Vishal Jain | 2019-08-17 | 2019-08-23 | 1 | 80% | bar: WEEK 5 F
1.1 | Applications | Sayali Kamble | 2019-08-17 | 2019-08-23 | 1 | 100% | bar: WEEK 5 F
2 | Project Design
2.1 | Proposed System | Sayali, Zahid, Vishal | 2019-08-24 | 2019-08-30 | 1 | 70% | bar: WEEK 6 M to WEEK 6 T
2.2 | Design(Flow Of Modules) | Sayali Kamble | 2019-08-24 | 2019-08-30 | 1 | 70% | bar: WEEK 6 T to WEEK 6 W
2.3 | Activity Diagram | Sayali Kamble | 2019-08-24 | 2019-08-30 | 1 | 50% | bar: WEEK 6 T to WEEK 6 R
2.4 | Use Case Diagram | Zahid khan | 2019-08-24 | 2019-08-30 | 1 | 50% | bar: WEEK 6 T to WEEK 6 R
2.5 | Description Of Use Case | Vishal Jain | 2019-08-24 | 2019-08-30 | 1 | 30% | bar: WEEK 6 R to WEEK 6 F
2.6 | Modules | Sayali, Zahid, Vishal | 2019-08-31 | 2019-09-20 | 3 | 30%
2.6.1 | Module-1 | Sayali Kamble | 2019-08-31 | 2019-09-20 | 3 | 30% | bar: WEEK 7 M to WEEK 8 W
2.6.2 | Module-2 | Zahid Khan | 2019-08-31 | 2019-09-20 | 3 | 30% | bar: WEEK 7 F to WEEK 9 W
2.6.3 | Module-3 | Vishal Jain | 2019-08-31 | 2019-09-20 | 3 | 30% | bar: WEEK 8 R to WEEK 9 F
2.7 | Preparation Of Report | Sayali, Zahid, Vishal | 2019-10-18 | 2019-10-25 | 1 | 80% | bar: WEEK 10 M to WEEK 10 F
3 | Project Implementation
3.1 | Module-1 |  |  |  | 0 | 0%
3.2 | Module-2 |  |  |  | 0 | 0%
3.3 | Module-3 |  |  |  | 0 | 0%
3.4 | Module-4 |  |  |  | 0 | 0%
4 | Testing
4.1 | Design of Test Cases |  |  |  | 0 | 0%
4.2 | Testing |  |  |  | 0 | 0%
5 | Results and Analysis
5.1 | Analysis Of Results |  |  |  | 0 | 0%
5.2 | Graphical Representation |  |  |  | 0 | 0%
5.3 | Report Preparation